## Acceptance Criteria
Type of Requirement | Acceptance Criteria ID | Component / Requirement | Detail from Requirement | Must / Should | Proofing Category (Proof by Test, Documentation, Demonstration, Codereview) | BDD Scenario Link to gitlab | BDD Scenarios | Delivered by (only filled if Proofing Category is "Documentation") | Remarks | Open Points for Refinement | Status
Functional Requirement | IDM.TRAIN.00014-A1 | Trust Framework Configuration | A request update of trust frameworks and DID configuration is successfully reflected in the DNS Zone File (200) | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/03-Trust-Framework-Configuration.feature/feature?ref_type=heads | 00014-A1_1 00014-A1_2 |  |  |  | Closed
Functional Requirement | IDM.TRAIN.00014-A2 | Trust Framework Configuration | An instantiation of a trust list is reflected in the trust list storage with possibility to retrieve via API endpoints | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/03-Trust-Framework-Configuration.feature/feature?ref_type=heads | 00014-A2 |  |  |  | Closed
Functional Requirement | IDM.TRAIN.00014-A3 | Trust Framework Configuration | Creation of a VC is allowed with ability to sign the credential | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/03-Trust-Framework-Configuration.feature/feature?ref_type=heads | 00014-A3 |  |  |  | Closed
Functional Requirement | IDM.TRAIN.00014-A4 | Trust Framework Configuration | A wrong context or missing data leads to an exception (400) | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/03-Trust-Framework-Configuration.feature/feature?ref_type=heads | 00014-A4 00014-A5 |  |  |  | Closed
Functional Requirement | IDM.TRAIN.00014-A5 | Trust Framework Configuration | An audit entry is created | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/03-Trust-Framework-Configuration.feature/feature?ref_type=heads | 00014-A4 00014-A5 |  | Logs are generated, which can be stashed and audited. |  | Closed
Functional Requirement | IDM.TRAIN.00014-A6 | Trust Framework Configuration | An error is provided if a record is in progress by the operator | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/03-Trust-Framework-Configuration.feature/feature?ref_type=heads | 00014-A6 |  |  |  | Closed
Functional Requirement | IDM.TRAIN.00014-A7 | Trust Framework Configuration | Should be able to reference Trust Frameworks from other Domains | Should | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/03-Trust-Framework-Configuration.feature/feature?ref_type=heads | 00014-A7 |  |  |  | Closed
Functional Requirement | IDM.TRAIN.00015-A1 | Trust List Management | A request update has been successfully reflected in the trust list (200) | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/02-Trust-List-Management.feature/feature?ref_type=heads | 00015-A1 bis 00015-A8 |  |  |  | Closed
Functional Requirement | IDM.TRAIN.00015-A2 | Trust List Management | A wrong context or missing data leads to an exception (400) | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/02-Trust-List-Management.feature/feature?ref_type=heads | 00015-A9 |  |  |  | Closed
Functional Requirement | IDM.TRAIN.00015-A3 | Trust List Management | Audit entry created | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/02-Trust-List-Management.feature/feature?ref_type=heads | 00015-A10 |  | Logs are generated, which can be stashed and audited. |  | Closed
Functional Requirement | IDM.TRAIN.00015-A4 | Trust List Management | Error, if record is in progress by the operator | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/02-Trust-List-Management.feature/feature?ref_type=heads | 00015-A11 |  |  |  | Closed
Functional Requirement | IDM.TRAIN.00015-A5 | Trust List Management | Integrate with the Notarization API | Must | Documentation |  |  | API Doc | Train is not actively using the Notary API. We have supplied our API Definition for integration to ECSEC |  | Closed
Functional Requirement | IDM.TRAIN.00016-A1 | Trusted Content Resolver (Trust Discovery) | Use standardized DNS resolvers | Must | Codereview | [5 empty] | Closed
Functional Requirement | IDM.TRAIN.00016-A2 | Trusted Content Resolver (Trust Discovery) | Use standardized DID resolver | Must | Codereview | [5 empty] | Closed
Functional Requirement | IDM.TRAIN.00016-A3 | Trusted Content Resolver (Trust Discovery) | Navigate multiple trust framework pointers | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/main/features?ref_type=heads | 00016-A3.1 00016-A3.2 |  | covered by: Testcase No.1 |  | Closed
Functional Requirement | IDM.TRAIN.00016-A4 | Trusted Content Resolver (Trust Discovery) | Discover different trust list formats | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/main/features?ref_type=heads | 00016-A4.1 00016-A4.2 |  |  |  | Closed
Functional Requirement | IDM.TRAIN.00016-A5 | Trusted Content Resolver (Trust Discovery) | Support different service types | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/main/features?ref_type=heads | 00016-A5 |  |  |  | Closed
Functional Requirement | IDM.TRAIN.00016-A6 | Trusted Content Resolver (Trust Discovery) | Optimized search mechanisms (e.g., Merkle Tree) | Must | Codereview | [5 empty] | Closed
Functional Requirement | IDM.TRAIN.00016-A7 | Trusted Content Resolver (Trust Discovery) | MUST Allow configuration of different DNS Name Servers | Must | Documentation |  |  | Installation Manual | https://gitlab.eclipse.org/eclipse/xfsc/train/trusted-content-resolver/-/tree/main/docs/install?ref_type=heads |  | Closed
Functional Requirement | IDM.TRAIN.00016-A8 | Trusted Content Resolver (Trust Discovery) | MUST allow configuration of user defined service content type (e.g., gxfs-trusted-issuer) | Must | Documentation |  |  | API Doc | https://gitlab.eclipse.org/eclipse/xfsc/train/trusted-content-resolver/-/tree/main/docs/rest_api?ref_type=heads |  | Closed
Functional Requirement | IDM.TRAIN.00016-A9 | Trusted Content Resolver (Trust Discovery) | The complete discovery process MUST be able to integrate with the TSA via libraries in GO, JAVA, Javascript, Python | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/main/features?ref_type=heads | 00016-A |  |  |  | Closed
Functional Requirement | IDM.TRAIN.00017-A1 | Trusted Content Resolver (Validation) | VC validation mechanism supports multiple signature proofs | Must | Codereview |  |  |  | We support: EdDSA, BBSPlus, RS256, ES256K (Ecdsa* variants) See TCR for implementation. |  | Closed
Functional Requirement | IDM.TRAIN.00017-A2 | Trusted Content Resolver (Validation) | Standardized open-source libraries for validation in GO, JAVA, Javascript, Python | Must | Documentation |  |  | API Doc | https://gitlab.eclipse.org/eclipse/xfsc/train/trusted-content-resolver/-/tree/main/docs/client_api?ref_type=heads |  | Closed
Functional Requirement | IDM.TRAIN.00017-A3 | Trusted Content Resolver (Validation) | OCI compliant containerization (Dockerized) | Must | Documentation |  |  | Installation Manual | https://gitlab.eclipse.org/eclipse/xfsc/train/trusted-content-resolver/-/tree/main/docs/install?ref_type=heads |  | Closed
Functional Requirement | IDM.TRAIN.00017-A4 | Trusted Content Resolver (Validation) | Resolve different trust strategies | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/04.2-Trusted-Content-Resolver_Verification.feature/feature | 00017-A1 |  | We assume this refers to recursive processing and discovery of the pointers, as well as the service endpoint types. |  | Closed
Functional Requirement | IDM.TRAIN.00017-A5 | Trusted Content Resolver (Validation) | Resolve multiple lists | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/04.2-Trusted-Content-Resolver_Verification.feature/feature | 00017-A1 |  |  |  | Closed
Functional Requirement | IDM.TRAIN.00017-A6 | Trusted Content Resolver (Validation) | Implement the resolving strategies | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/04.2-Trusted-Content-Resolver_Verification.feature/feature | 00017-A1 |  |  |  | Closed
Functional Requirement | IDM.TRAIN.00017-A7 | Trusted Content Resolver (Validation) | The complete validation process of the Trusted Content Resolver MUST be able to integrate with the TSA via libraries in GO, JAVA, Javascript, Python | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/04.2-Trusted-Content-Resolver_Verification.feature/feature | 00017-A1 |  |  |  | Closed
Functional Requirement | IDM.TRAIN.00018-A1 | Translate XML | This functionality at Trusted Content Resolver is responsible for detecting and translating the format of the trust list. | MUST | Documentation |  |  | API Doc | https://gitlab.eclipse.org/eclipse/xfsc/train/trusted-content-resolver/-/tree/main/docs/rest_api?ref_type=heads |  | Closed
Functional Requirement | IDM.TRAIN.00019-A1 | Translate JSON | This functionality at Trusted Content Resolver is responsible for detecting and translating the format of the trust list. | MUST | Documentation |  |  | API Doc | https://gitlab.eclipse.org/eclipse/xfsc/train/trusted-content-resolver/-/tree/main/docs/rest_api?ref_type=heads |  | Closed
Functional Requirement | IDM.TRAIN.00020-A1 | TSPA (Zone Manager Handler) | The TSPA MUST be able to configure the Zone Manager using the Zone Manager Handler. | Must | Demonstration | [5 empty] | Closed
Functional Requirement | IDM.TRAIN.00021/22/23-A1 | Fedaration/Participant/Organisation specific Framework and Trust List | Analysis with existing standards (e.g., ETSI, NIST, etc.) | Must | Documentation |  |  | Trust List Model document | https://gitlab.eclipse.org/eclipse/xfsc/train/tspa/-/tree/master/doc/TrustList_DataModel_Design?ref_type=heads |  | Closed
Functional Requirement | IDM.TRAIN.00021/22/23-A2 | Fedaration/Participant/Organisation specific Framework and Trust List | Trust list data model in JSON and XML format with proper semantics | Must | Documentation |  |  | Trust List Model document | https://gitlab.eclipse.org/eclipse/xfsc/train/tspa/-/tree/master/doc/TrustList_DataModel_Design?ref_type=heads |  | Closed
Functional Requirement | IDM.TRAIN.00021-A3 | Federation specific Framework and Trust Lists | Address three use cases (i.e., Automotive, IIOT, Dataspaces ) | Must | Documentation |  |  | Trust List Model document | https://gitlab.eclipse.org/eclipse/xfsc/train/tspa/-/tree/master/doc/TrustList_DataModel_Design?ref_type=heads |  | Closed
Functional Requirement | IDM.TRAIN.00022-A3 | Participant specific Framework and Trust List | Address three use cases for different participants | Must | Documentation |  |  | Trust List Model document | https://gitlab.eclipse.org/eclipse/xfsc/train/tspa/-/tree/master/doc/TrustList_DataModel_Design?ref_type=heads |  | Closed
Functional Requirement | IDM.TRAIN.00023-A3 | Organization specific Framework and Trust List | Address three use cases for different organizations | Must | Documentation |  |  | Trust List Model document | https://gitlab.eclipse.org/eclipse/xfsc/train/tspa/-/tree/master/doc/TrustList_DataModel_Design?ref_type=heads |  | Closed
Functional Requirement | IDM.TRAIN.00024-A1 | Zone Manager | A request update has been successfully reflected in the sqlite storage and Zone file (200) | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/01-DNS-Zone-Manager.feature/features?ref_type=heads | 00024-A1 00024-A2 |  |  |  | Closed
Functional Requirement | IDM.TRAIN.00024-A2 | Zone Manager | A wrong context or missing data leads to an exception (400) | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/01-DNS-Zone-Manager.feature/features?ref_type=heads | 00024-A3 |  |  |  | Closed
Functional Requirement | IDM.TRAIN.00024-A3 | Zone Manager | An audit entry is created | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/01-DNS-Zone-Manager.feature/features?ref_type=heads | 00024-A4 |  | Logs are generated which can be stashed and audited |  | Closed
Functional Requirement | IDM.TRAIN.00024-A4 | Zone Manager | An error, if record is in progress by the operator | Must | BDD Testscripts | https://gitlab.eclipse.org/eclipse/xfsc/train/BDD/-/tree/01-DNS-Zone-Manager.feature/features?ref_type=heads | 00024-A5 |  |  |  | Closed
Functional Requirement | IDM.TRAIN.00024-A5 | Zone Manager | MUST integrate with the TSPA Manager using the Zone Manager Handler | Must | Documentation |  |  | Project General/Arch Docs | https://gitlab.eclipse.org/eclipse/xfsc/train/TRAIN-Documentation/-/tree/main/architecture?ref_type=heads |  | Closed
Functional Requirement | IDM.TRAIN.00024-A6 | Zone Manager | MUST be tested with NSD & KNOT DNS Servers | Must | Demonstration |  |  |  | KNOT has been removed. |  | Closed
Functionality Acceptance Criteria | IDM.TRAIN.00062 | Zone Manager/TSPA Configuration | A domain was registered, and a DNSSec Server is linked to it. The product Zone Manager was installed on a machine, and it MUST be possible to link the Zone Manager with the DNSSec Server. The Zone Manager Handler MUST be configured to allow access to the zone manager (internal API). After this, using TSPA Trust Frameworks and DIDs can be published over the Zone Manager Handler into the zone file. After the rollout, using the endpoints of the TSPA with Dig commands and queries, the Trust Framework and DID (PTR and URI RR) of the Zone File are resolvable. | Must | Demonstration |  |  |  | we assume the test case is covered by above acceptance criteria - mapping to be done |  | Closed
Functionality Acceptance Criteria | IDM.TRAIN.00063 | Trust Zone Demonstration | Trusted Content publishing and resolution MUST be demonstrated over a public domain with DNSsec functionality. Various entries MUST be added to the zone and be resolved by the Trusted Content Resolver. | Must | Demonstration |  |  |  | we assume the test case is covered by above acceptance criteria - mapping to be done |  | Closed
Functionality Acceptance Criteria | IDM.TRAIN.00064 | Trust Framework cross-linking Demonstration | Cross-linking of Trust Frameworks MUST be demonstrated over two public domains with DNSsec functionality. A cross-link from one trust framework on domain 1 (using the PTR Record) MUST reference another Trust Framework on domain 2. Various entries MUST be added to the Trust Frameworks on domain 1 and domain 2 and be correctly resolved by the Trusted Content Resolver | Must | Demonstration |  |  |  | Covered by having separate frameworks in train1, in the same zonemanager. DNS resolving works exactly the same way as if it were different domains. |  | Closed
Functionality Acceptance Criteria | IDM.TRAIN.00065 | Trust Framework and DID Enrollment | Trust Frameworks and their corresponding DIDs MUST be enrolled using API endpoints offered by the TSPA. The enrolled details MUST be reflected in the database and the DNS Zone file of the Name server | Must | Demonstration |  |  |  | we assume the test case is covered by above acceptance criteria - mapping to be done |  | Closed
Functionality Acceptance Criteria | IDM.TRAIN.00066 | Trusted List Management using API endpoints | The Trust List content MUST be managed using API endpoints. Separate API endpoints MUST be available for performing CRUD Operations. | Must | Documentation |  |  | API Doc | we assume the test case is covered by above acceptance criteria - mapping to be done |  | Closed
Functionality Acceptance Criteria | IDM.TRAIN.00067 | Trusted Content Resolver resolves Trust Zone Pointers | The trusted content resolver is called by a Trust Framework Pointer (URL/DNS Name). The resolver recognizes that a DNS query must be made and it’s starting to resolve the records about other Trust Framework Pointers (if applicable). After resolving the entire Zone, the DIDs of the RR/URI Records can be resolved as usual. Output is a List of Pointers which the resolver returns. | Must | To be refined |  |  |  | The specification clearly states that the resolving sequence continues until the trust list level is reached. Expected output of the resolver are all relevant trust lists, with their enveloping vcs and their dids. We read the spec as: TCR will resolve and afterwards directly validate: "The inputs for validation are based on the output of the trust discovery functionality". Also see 5.5 Trust Verification in Trust Management for GX, the verification process is described as one self-contained process. | We can showcase that resolving and verification work, but not as stated in this specific requirement, as it is in conflict with the specification | Closed
Functionality Acceptance Criteria | IDM.TRAIN.00068 | Trusted Content Resolver resolves Trusted Content | The trusted content resolver is called by a DID, and a list of requested content types. The resolver resolves the DID, iterates through the service endpoint references, and returns a list of trust lists (no DID documents), regarding the given DID. The DID documents for the resolved references can be found in a second list. | Must | To be refined |  |  |  | Resolving directly from a DID is not contained within the spec, or the extended architecture and definitions of TRAIN. Seciton 5.5 Trust Verification of "Trust Management Infrastructure for GX" specified explicitly that a Framework pointer as a DNS name is the basis for trust resolving. | We can showcase that resolving and verification work, but not as stated in this specific requirement, as it is in conflict with the specification, but with framework pointers instead. | Closed
Functionality Acceptance Criteria | IDM.TRAIN.00069 | Trusted Content Resolver validates institutional trust of a Verifiable Credential | The issuer details of a credential MUST be validated with the resources found from the Trust List. This MUST be demonstrated with Trust Frameworks that are cross-linked to other Trust Frameworks (hosted on different domains) as well as Trust Frameworks that do not include a cross-linking. This MUST be available as integratable libraries for programming languages GO, Javascript, Python and Java | Must | Demonstration |  |  |  | we assume the test case is covered by above acceptance criteria - mapping to be done |  | Closed
Functional Requirement | IDM.TRAIN.00003-A1 | Kubernetes Environment | Be able to run on standard Kubernetes based environments. | Must | Codereview | [5 empty] | Closed
Functional Requirement | IDM.TRAIN.00003-A2 | Kubernetes Environment | Be able to run on SCS Cluster provided by contractor | Must | Demonstration | [5 empty] | Closed
Non-Functional Requirement | IDM.TRAIN.00004-A1 | Adminstration Documentation | Documentation contains Items listed under IDM.TRAIN.0004 | Must | Documentation |  |  | Installation Manual | Installation Manual for Zone Manager Installation Manual for TSP Manager |  | Closed
Non-Functional Requirement | IDM.TRAIN.00004-A2 | Adminstration Documentation | Documentation contains Items listed under IDM.TRAIN.0004 | Must | Documentation |  |  | Operations Manual | Administrative User Documentation for Trust Framework Configuration Administrative User Documentation for Trust List Management |  | Closed
Non-Functional Requirement | IDM.TRAIN.00004-A3 | Adminstration Documentation | Documentation contains Items listed under IDM.TRAIN.0004 | Must | Documentation |  |  | Operations Manual | Operational Runbook: Compilation/Build and Deployment of DNS Zone Manager Operational Runbook: Compilation/Build and Deployment of TSPA https://gitlab.eclipse.org/eclipse/xfsc/train/trusted-content-resolver/-/tree/main/docs/install?ref_type=heads |  | Closed
Non-Functional Requirement | IDM.TRAIN.00004-A5 | Adminstration Documentation | Documentation contains Items listed under IDM.TRAIN.0004 | Must | Documentation |  |  | Project General/Arch Docs | Testing Specification: Coverung Automated Testing Process and Test Verification |  | Closed
Non-Functional Requirement | IDM.TRAIN.00005-A1 | User Documentation | Documentation contains Items listed under IDM.TRAIN.0005 | Must | Documentation |  |  | User Doc | User Documentation: Software Description User Documentation: TCR https://gitlab.eclipse.org/eclipse/xfsc/train/trusted-content-resolver/-/tree/main/docs/rest_api?ref_type=heads & https://gitlab.eclipse.org/eclipse/xfsc/train/trusted-content-resolver/-/tree/main/docs/client_api?ref_type=heads User Documentation: Notarization Service: TRAIN - Trust Zone Management User Documentation: FAQ, Keyword List |  | Closed
Non-Functional Requirement | IDM.TRAIN.00005-A2 | User Documentation | Documentation contains Items listed under IDM.TRAIN.0005 | Must | Documentation |  |  | API Doc | Administrative User Documentation: TRAIN Integration in TSA, OCM, PCM |  | Closed
Non-Functional Requirement | IDM.TRAIN.00005-A3 | User Documentation | Documentation contains Items listed under IDM.TRAIN.0005 | Must | Documentation |  |  | API Doc | https://gitlab.eclipse.org/eclipse/xfsc/train/trusted-content-resolver/-/tree/main/docs/client_api?ref_type=heads |  | Closed
Non-Functional Requirement | IDM.TRAIN.00005-A4 | User Documentation | Documentation contains Items listed under IDM.TRAIN.0005 | Must | Documentation |  |  | Operations Manual | Operational Handbook: Components and Operational Interactions, Security Concept, https://gitlab.eclipse.org/eclipse/xfsc/train/TRAIN-Documentation/-/tree/main/concepts/gdpr?ref_type=heads |  | Closed
Non-Functional Requirement | IDM.TRAIN.00006-A1 | Trust Framework Configuration UI | The product MUST provide a Web UI which allows the administrator to add new trust frameworks and corresponding DIDs. | Must | Demonstration | [5 empty] | Closed
Non-Functional Requirement | IDM.TRAIN.00007-A1 | Trust Zone Visualization UI | The product MUST provide a Web UI which visualizes the content of a trustzone (e.g., zones, pointers, DIDs etc.) for external/public users. | Must | Demonstration | [5 empty] | Closed
Non-Functional Requirement | IDM.TRAIN.00008-A1 | Universal did resolver | The DIF Universal Resolver is the product basis that is used for resolving trusted content of DIDs. For building the trusted content resolver, this software is the basis that is to be enhanced. | Must | Codereview | [5 empty] | Closed
Non-Functional Requirement | IDM.TRAIN.00009-A1 | DNS Resolver | An Open-Source DNS Resolver MUST be used to discover PTR, URI, DNSSEC Resource Records (RR). And this MUST be integrated with Trusted Content Resolver. | Must | Codereview | [5 empty] | Closed
Functional Requirement | IDM.TRAIN.00010-A1 | Authoritative DNSSec Servers | DNS Name Servers such as NSD and KNOT DNS MUST be used and tested for DNS Zone installation and configuration. | Must | Demonstration |  |  |  | Can only demonstrate for NSD. As demonstration requires deployment, which cannot be done for KNOT due to the GPL license restrictions on distribution. |  | Closed
Non-Functional Requirement | IDM.TRAIN.00011-A1 | Cryptographic Libraries | Open-Source Cryptographic libraries compliant with the BSI5 and EU DSS6 rules including BSI TR-02102-17 MUST be used for VC/trustlist signing, VC / trustlist proof validation and DNSSEC Trust Chain Validation. | Must | Codereview |  |  |  | Some de-facto standard signature algos are not yet recommented by BSI. This is further covered in the security concept |  | Closed
Non-Functional Requirement | IDM.TRAIN.00012-A1 | Eventing | If the use of events within the software architecture is required, it is mandatory to use software abstraction according to CloudEvents specification for publishing and subscription. The minimal supported protocol binding MUST be HTTP and JSON Protocol Binding. | Must | Codereview |  |  |  | No events are used. |  | Closed
Non-Functional Requirement | IDM.TRAIN.00013-A1 | Eventing Infrastructure | The event broker for the eventing MUST abstract the storage and delivery infrastructure. In Kubernetes environments, the broker MUST be uniform across all Lots. (e.g., Knative) | Must | Codereview |  |  |  | No events are used. |  | Closed
Non-Functional Requirement | IDM.TRAIN.00025-A1 | Non -Functional Requirements | Endpoints protected by TLS1.2 | Must | Codereview |  |  |  | protection through kubernetes ingress. Nginx uses tsl1.2 or greater by default |  | Closed
Non-Functional Requirement | IDM.TRAIN.00025-A2 | Non -Functional Requirements | TLS Certificates confgurable by Administrator | Must | Documentation |  |  | Installation Manual | handled by kubernetes ingress. |  | Closed
Non-Functional Requirement | IDM.TRAIN.00026-A1 | Non -Functional Requirements | HTTP endpoints standardization based on RFCs 7231, 5789 and 7808 | Must | Documentation |  |  | API Doc |  |  | Closed
Non-Functional Requirement | IDM.TRAIN.00027-A1 | Non -Functional Requirements | GDPR Compliance for Logging. All logged data must be documented in GPDR design decisions | Must | Documentation |  |  | GDPR Compliance Document |  |  | Closed
Non-Functional Requirement | IDM.TRAIN.00028-A1 | Non -Functional Requirements | Use logging frameworks supporting OpenTelementry | Must | Codereview |  |  |  | We are using slf4j, which enables a switch to logstash or any other desired logging framework without code changes. For demo deployment we just log to console. |  | Closed
Non-Functional Requirement | IDM.TRAIN.00028-A2 | Non -Functional Requirements | Operations concept must sketch how support of multiple solutions in the future | Must | Codereview |  |  | Operations Manual | Using slf4j, makes it easy to switch between logging solution |  | Closed
Non-Functional Requirement | IDM.TRAIN.00029-A1 | Non -Functional Requirements | Components must be able to scale for an undefined amount of instances | Must | Demonstration |  |  |  | Can show with arbitrary numbers. |  | Closed
Non-Functional Requirement | IDM.TRAIN.00030-A1 | Non -Functional Requirements | Services must be provided OCI containerized. | Must | Documentation |  |  | Installation Manual |  |  | Closed
Non-Functional Requirement | IDM.TRAIN.00030-A2 | Non -Functional Requirements | DNS Zone Manager must be tested with core DNS Kubernetes | Must | Not Applicable |  |  |  | We assume coreDNS is a legacy wording. Requirements state compatibility with KNOT DNS and NSD. |  | Closed
Non-Functional Requirement | IDM.TRAIN.00031-A1 | Non -Functional Requirements | DNS Zone Manager must be able to integrate Trust Framework and Trust List Provision Services | Must | Documentation |  |  | Installation Manual |  |  | Closed
Non-Functional Requirement | IDM.TRAIN.00032-A1 | Non -Functional Requirements | The Trusted Content Resolver MUST be able to resolve DNS Queries and MUST be able to fetch and verify trust framework and trust list provision services | Must | Demonstration | [5 empty] | Closed
Non-Functional Requirement | IDM.TRAIN.00033-A1 | Non -Functional Requirements | All used software components MUST use the major releases with Long Term Support (LTS). If no LTS is available, all components MUST use the latest major releases with security hardening | Must | Codereview |  |  |  | See license report |  | Closed
Non-Functional Requirement | IDM.TRAIN.00034-A1 | Non -Functional Requirements | All software components MUST have applied CVE patches, which are available for major releases. | Must | Codereview |  |  |  | See security scans in gitlab |  | Closed
Non-Functional Requirement | IDM.TRAIN.00035-A1 | Non -Functional Requirements | An adequate security risk management process is applied compliant to EU ENISA Risk Management in usage of a Tread Modelling Process like PASTA or OWSAP | Must | Documentation |  |  | Security Concept | The scurity concept will only describe the risk management process. Applying it on production is responsibility of the operating entity. |  | Closed
Non-Functional Requirement | IDM.TRAIN.00035-A2 | Non -Functional Requirements | All software components MUST be compliant to the requirements of the Pentesting like BSI IS-Penetrationstest | Must | Documentation |  |  | Pentesting Report | See security concept |  | Closed
Non-Functional Requirement | IDM.TRAIN.00036-A1 | Non -Functional Requirements | All software components MUST be compliant to the requirements within the quality assurance repository | Must | Not Applicable |  |  |  | It is unclear how proof of compliance could be achieved, as the repository lacks definitions and objectively provable criteria and clear descriptions on how to prove in a non obtrusive way. Refining those should be in the responsibility of Eco/Program Management. We will work in a compliant way nonetheless. |  | Closed
Non-Functional Requirement | IDM.TRAIN.00037-A1 | Non -Functional Requirements | The used technologies MUST have consistency. Standard technologies e.g., databases MUST be abstracted over JDBC, authentication over OIDC etc. | Must | Codereview | [5 empty] | Closed
Non-Functional Requirement | IDM.TRAIN.00038-A1 | Non -Functional Requirements | All components and the entire software architecture MUST be checked for the necessity for deployment of each single feature, to allow enterprise deployment customization. | Must | Documentation |  |  | Installation Manual |  |  | Closed
Non-Functional Requirement | IDM.TRAIN.00039-A1 | Non -Functional Requirements | The seven EU GDPR principles MUST be considered: | Must | Documentation |  |  | GDPR Compliance Document | https://gitlab.eclipse.org/eclipse/xfsc/train/TRAIN-Documentation/-/tree/main/concepts/gdpr?ref_type=heads |  | Closed
Non-Functional Requirement | IDM.TRAIN.00040-A1 | Non -Functional Requirements | Is it necessary to process person-relevant data, it MUST be earmarked to a clearly defined business process, which has to be described in the GDPR design decisions. All relevant data MUST be deleted after the processing, if applicable. | Must | Documentation |  |  | GDPR Compliance Document | https://gitlab.eclipse.org/eclipse/xfsc/train/TRAIN-Documentation/-/tree/main/concepts/gdpr?ref_type=heads |  | Closed
Non-Functional Requirement | IDM.TRAIN.00041-A1 | Non -Functional Requirements | All installations MUST be scripted/templated to ensure automated deployment into an enterprise Kubernetes cluster (K8S), SCS K8S demonstration cluster and local K8S development instance. This MUST be ensured uniform over HELM templates which MUST follow uniform across all lots (orientation on existing deployment pipelines from phase I and with alignment with the contractor). The charts MUST be integrable in a ARGO CD Pipeline defined in the gxfs-integration repository | Must | Documentation |  |  | Installation Manual | See each component install manual |  | Closed
Non-Functional Requirement | IDM.TRAIN.00042-A2 | Non -Functional Requirements | If environment variables are overwriting an actively set configuration, a warning SHOULD be logged | Must | Codereview | [5 empty] | Closed
Non-Functional Requirement | IDM.TRAIN.00042-A1 | Non -Functional Requirements | All components MUST support one of the major configuration formats (yaml, json, ini, environment variables) wherever configuration is required. | Must | Documentation |  |  | Installation Manual | See each component install manual |  | Closed
Non-Functional Requirement | IDM.TRAIN.00043-A1 | Non -Functional Requirements | All component helm charts MUST be available under a helm repository hosted in the gitlab, with different channels for distribution | Must | Codereview |  |  |  | Helm charts are available under each components repo, in deploy/helm |  | Closed
Non-Functional Requirement | IDM.TRAIN.00044-A1 | Non -Functional Requirements | Additionally, the Charts MUST provide Istio Resource (e.g., Authorization Rules, Virtual Services etc.) following the integration pattern specified in the gxfs-integration repo | Must | Not Applicable |  |  |  | ISTIO wurde von ECO bisher nicht bereitgestellt. Es ist daher nicht möglich dieses Requirement zu testen, bzw einzuhalten. |  | Closed
Non-Functional Requirement | IDM.TRAIN.00045-A1 | Non -Functional Requirements | All HELM charts MUST be provided with Istio support aligned together with the contractor. This consists of Authorization Rules, Virtual Service Definitions and other relevant Istio Definitions which are required for integration in a Istio Environment. | Must | Not Applicable |  |  |  | ISTIO wurde von ECO bisher nicht bereitgestellt. Es ist daher nicht möglich dieses Requirement zu testen, bzw einzuhalten. |  | Closed
Non-Functional Requirement | IDM.TRAIN.00046-A1 | Non -Functional Requirements | Each development MUST consider the following standard technologies if nothing else is explicitly requested | Must | Codereview | [5 empty] | Closed
Non-Functional Requirement | IDM.TRAIN.00047-A1 | Non -Functional Requirements | All helm charts/services MUST provide metrics endpoints in opentelemetry format | Must | Codereview |  |  |  | TCR and TSPA use micrometer to expose metrics. Uis do not require metrics, as they are mainly intended to be used for demonstration purposes. Zonemanager is unclear what metrics are important/interesting. Zonemanager provides availability metrics as a health check route. |  | Closed
Non-Functional Requirement | IDM.TRAIN.00048-A1 | Non -Functional Requirements | Environment specific parameters MUST be configurable over the helm templates by using profiles. Each component MUST be delivered minimum for profile: - DEV, a local environment for round trip development and testing - Acceptance, a restricted resource environment (with minimal system requirements) which can be deployed in cluster (remote or locally) - Prod, a scalable environment with fault tolerance, HA settings and security hardening | Must | Documentation |  |  | Installation Manual | See each component install manual |  | Closed
Non-Functional Requirement | IDM.TRAIN.00049-A1 | Non -Functional Requirements | The configuration secrets within Helm Charts MUST use secretRefs to support external Secret Management. Clear text secrets within the Helm Charts are not allowed | Must | Codereview |  |  |  | Secrets are added through argocd, and are not visible in the helm charts, but in the final deployment yaml files only through argocd |  | Closed
Non-Functional Requirement | IDM.TRAIN.00050-A1 | Non -Functional Requirements | For a better scale out, maintainability and decentralization, the product architecture MUST have a microservice architecture. Each microservice MUST NOT be limited on the lines of code or number of days to implement. The service “size” SHOULD be oriented on the fine granular business capabilities. (e.g., Order, ListMenu, Payment) | Must | Documentation |  |  | Project General/Arch Docs | https://gitlab.eclipse.org/eclipse/xfsc/train/TRAIN-Documentation/-/tree/main/architecture?ref_type=heads |  | Closed
Non-Functional Requirement | IDM.TRAIN.00051-A1 | Non -Functional Requirements | To support the microservice architecture within the maintainability, a domain model MUST be declared before realization. The software description MUST explain which domain model was chosen, which services contain it and how it scales. This MUST be documented in the public code repository to support future enhancements for new developers | Must | Documentation |  |  | Project General/Arch Docs | https://gitlab.eclipse.org/eclipse/xfsc/train/TRAIN-Documentation/-/tree/main/architecture?ref_type=heads |  | Closed
Non-Functional Requirement | IDM.TRAIN.00052-A1 | Non -Functional Requirements | All components MUST be reusable in different enterprise environments by customization and whitelabeling. This means that all components MUST be able to customize and white label the components by configuration settings (e.g., UIs, text labels, endpoints etc.) | Must | Documentation |  |  | Installation Manual | https://gitlab.eclipse.org/eclipse/xfsc/train/TRAIN-Documentation/-/tree/main/architecture?ref_type=heads |  | Closed
Non-Functional Requirement | IDM.TRAIN.00053-A1 | Non -Functional Requirements | All components MUST reflect - after bootstrap and during runtime - the correctness of the service functionality by reflecting it over health endpoints. The health endpoint MUST return failure (red), if any internal behavior failure or misconfiguration occurs (not just the software running state). This means for instance to check continuously during runtime: - An unreachable configured Services results in failed state - Configured Service Endpoints need to be checked for readiness during runtime, if not reachable, it results in failure state - Check dependent components (Database, Microservice etc.) behind it, if not reachable, it results in failed state | Must | Demonstration | [5 empty] | Closed
Non-Functional Requirement | IDM.TRAIN.00054-A1 | Non -Functional Requirements | Each deployment MUST be configured for a minimum fault tolerance of 2 instances | Must | Codereview |  |  |  | Configurable through HELM Charts. |  | Closed
Non-Functional Requirement | IDM.TRAIN.00055-A1 | Non -Functional Requirements | All Architecture Changes MUST be aligned with the contractor before implementation. | Must | Documentation |  |  | Change Requests |  |  | Closed
Non-Functional Requirement | IDM.TRAIN.00056-A1 | Non -Functional Requirements | If the verification is related to software components, it MUST be deployed in a k8s test cluster and the components must be deployable in a Kubernetes cluster with automated package manager deployment (e.g., Helm). | Must | Documentation |  |  | Installation Manual | See ech component install manual |  | Closed
Non-Functional Requirement | IDM.TRAIN.00057-A1 | Non -Functional Requirements | All eventings MUST be demonstrated based on cloud events specifications together with the kNative broker in a Kubernetes environment | Must | Demonstration |  |  |  | No eventings in TRAIN |  | Closed
Non-Functional Requirement | IDM.TRAIN.00058-A1 | Non -Functional Requirements | Each service MUST be demonstrated up and running in Kubernetes, configured by config maps. | Must | Documentation |  |  | Installation Manual |  |  | Closed
Non-Functional Requirement | IDM.TRAIN.00059-A1 | Non -Functional Requirements | The service installation MUST be demonstrated during HELM install | Must | Documentation |  |  | Installation Manual |  |  | Closed
Non-Functional Requirement | IDM.TRAIN.00060-A1 | Non -Functional Requirements | The helm chart MUST be able to install inside of argoCD. This includes the usage of the postgres hooks and the provisioning of usable values.yaml(s) for all developed services | Must | Documentation |  |  | Installation Manual | See ech component install manual |  | Closed
Non-Functional Requirement | IDM.TRAIN.00061-A1 | Non -Functional Requirements | All HELM installations MUST run on SCS (Sovereign Cloud Stack). The final acceptance demonstration cannot be realized on azure, google cloud etc | Must | Demonstration | [5 empty] | Closed

## Input Output
Input Output ID | Input | Output |  | Component
IDM.TRAIN.00014-IO1 | Trust Framework enrollment | Creation of Trust Framework as PTR record in DNS |  | Trust Framework Configuration
IDM.TRAIN.00014-IO2 | DID enrollment | DID enrolled as URI RR mapped with corresponding Trust Framework |  | Trust Framework Configuration
IDM.TRAIN.00014-IO3 | Envelope Trust List Endpoint | Verifiable Credential with Trust List endpoint as Credential Subject |  | Trust Framework Configuration
IDM.TRAIN.00014-IO4 | Instantiating Trust List (Storage at Web Server or IPFS) | Trust List published in storage with retrievable API endpoint |  | Trust Framework Configuration
IDM.TRAIN.00015-IO1 | A confirmed request record. This MUST include: 1. DID of the organization 2. URI of the trust list 3. URI of the schema 4. Metadata of the entity (to be specified further according to business analyst analysis) ○ Legal Name ○ Certification details ○ Assurance Levels 5. Configure supported DID methods 6. Type of other digital credentials supported (example: x509) 7. Different services offered by the organization | In create operation: a new trust list entry MUST be created | Must | Trust List Management
IDM.TRAIN.00015-IO2 |  | In read operation: the API endpoints MUST have the flexibility to read the whole trust list and also separate entities using UUID | Must | Trust List Management
IDM.TRAIN.00015-IO3 |  | In update operation: the change requested by the user MUST be reflected in trust list | Must | Trust List Management
IDM.TRAIN.00015-IO4 |  | In delete operation: the trust list entry of the entity MUST be deleted from the list | Must | Trust List Management
IDM.TRAIN.00015-IO5 |  | Must contain auditing mechanisms for the trust list. Please refer to the trust concept document [GX.TRUST] for different mechanisms listed there. | Must | Trust List Management
IDM.TRAIN.00016-IO1 | Trust Framework Pointer (e.g., example.federation1.de) + Types to be considered | Corresponding DID mapped to Trust Framework Pointer |  | Trusted Content Resolver (Trust Discovery)
IDM.TRAIN.00016-IO2 | Issuer details from the VC/VP (e.g., DID/URI) | DID Document of the DID |  | Trusted Content Resolver (Trust Discovery)
IDM.TRAIN.00016-IO3 | ServiceType of the trust list (e.g., issuance service, verifier service) | Trust List VC endpoint |  | Trusted Content Resolver (Trust Discovery)
IDM.TRAIN.00017-IO1 | Corresponding DID mapped to Trust Framework Pointer | Validation result of VC |  | Trusted Content Resolver (Validation)
IDM.TRAIN.00017-IO2 | DID Document of the DID | Validation result of Issuer details (present/not present) |  | Trusted Content Resolver (Validation)
IDM.TRAIN.00017-IO3 | Trust List VC endpoint | If Issuer details are found, display meta data information, public keys, schema from the trust list |  | Trusted Content Resolver (Validation)
IDM.TRAIN.00021-IO1 | No Input | The Trust List Data model MUST cover the following aspects in detail: 1. Business rules 2. Federation meta data (e.g., legal name, etc.) 3. Accommodate different identifiers (e.g., LEI - Legal Entity Identifier) 4. Accommodate assurance levels 5. Accommodate different digital identities (e.g., DID, PKI) 6. Different services offered by the federation 7. Accommodate auditable history information URI in trust list |  | Federation specific Framework and Trust List
IDM.TRAIN.00022-IO1 | No Input | The Trust List Data model MUST cover the following aspects in detail: 1. Business rules 2. Participant meta data (e.g., legal name, etc.) 3. Accommodate different identifiers (e.g.: LEI) 4. Accommodate assurance levels 5. Accommodate different digital identities (e.g., DID, PKI) 6. Different services trusted by the participant 7. Accommodate auditable history information URI in trust list |  | Participant specific Framework and Trust List
IDM.TRAIN.00023-IO1 | No Input | The Trust List Data model MUST cover the following aspects in detail. 1. Business rules 2. Organization meta data (e.g., legal name, etc.) 3. Accommodate different identifiers (e.g., LEI) 4. Accommodate assurance levels 5. Accommodate different digital identities (e.g., DID, PKI) 6. Different services offered by the organization 7. Accommodate auditable history information URI in trust list |  | Organization specific Frameworks and Trust Lists
IDM.TRAIN.00024-IO1 | Trust Framework | Update of Trust Framework and DID in the DNS Zone file |  | Zone Manager
IDM.TRAIN.00024-IO2 | DID Enrollment corresponding to Trust Framework | Update of Trust Framework and DID in the DNS Zone file |  | Zone Manager

## Defaults
proof-type-values | documentation artifacts:
BDD Testscripts | Installation Manual
Documentation | Operations Manual
Demonstration | Project General/Arch Docs
Codereview | API Doc
Not Applicable | GDPR Compliance Document
To be refined | Trust List Model document
User Doc
Pentesting Report
Change Requests
Security Concept